## Automation_Dev_Sprint_Plan
Sl.No | High Level Work Items | Low Level Activities | Dependencies | Panel | Deliverables | Sprints (1 sprint = 2 Weeks) | Status | Sprint Start Date | Sprint End Date | Release | Backlogs | Remarks
1 | 1. Test plan walkthrough 2. Automation test bed preparation and configuration 3. Automation of sanity test cases - 50%. | Automation Development: 1. Test plan walkthrough 2. Creating the automation procedure/steps/commands for the test cases. 3. Test bed setup and configuration 4. Checking the feasibility of the existing automation framework for re-use. 5. Nose framework will be used. 6. Support of Allure report 7. Unit testing and sanity testing 8. Bug reporting and fixing Note: Sniffer support is not part of this release Test engineer: 1. Regression run. Dev Engineer Support: 1. Support the automation team by clarifying doubts/issues with respect to panel and cameras, which are identified by the automation team 2. Debug the panel and the camera failures by helping automation team | 1. Test Plan 2. Panel: SC 3. Cameras: Ping, dbc, hdc300, hdc400, hd450+bridge 4. All testbed accessaries (Home AP, USB hub, Eth Switch, Sniffer machine) | SkyControl | 1. Framework code drop into bitbucket 2. Test automation coverage/report | 1 | Completed | 2019-05-15 | 2019-05-28 | GES_VIVINT_REGRESSION_AUTO_V1.0.0
2 | Sanity automation - 100% Functionality automation - 50 % | Automation Development: 1. Creating the automation procedure/steps/commands for the test cases. 2. Checking the feasibility of the existing automation framework for re-use. 3. Sniffer module enhancement 4. Unit testing and sanity testing 5. Bug reporting and fixing Test engineer: 1. Regression run. Dev Engineer Support: 1. Support the automation team by clarifying doubts/issues with respect to panel and cameras, which are identified by the automation team 2. Debug the panel and the camera failures by helping automation team | 1. Test Plan 2. Panel: SC 3. Cameras: Ping, dbc, hdc300, hdc400, hd450+bridge | SkyControl | 1. Framework code drop into bitbucket 2. Test automation coverage/report | 2 | In-Progress | 2019-05-29 | 2019-06-11
3 | Functionality automation - 100 % Stress & Stability - 50% | Automation Development: 1. Creating the automation procedure/steps/commands for the test cases. 2. Functionality and SnS test automation 3. Sniffer module enhancement 4. Unit testing and sanity testing 5. Bug reporting and fixing Test engineer: 1. Regression run. Dev Engineer Support: 1. Support the automation team by clarifying doubts/issues with respect to panel and cameras, which are identified by the automation team 2. Debug the panel and the camera failures by helping automation team | 1. Test Plan 2. Panel: SC 3. Cameras: Ping, dbc, hdc300, hdc400, hd450+bridge | SkyControl | 1. Framework code drop into bitbucket 2. Test automation coverage/report | 3 |  | 2019-06-12 | 2019-06-25
4 | Stress & Stability - 100% Reliability - 50% | Automation Development: 1. Creating the automation procedure/steps/commands for the test cases. 2. SnS and reliability test automation 3. Sniffer module enhancement 4. Unit testing and sanity testing 5. Bug reporting and fixing Test engineer: 1. Regression run. Dev Engineer Support: 1. Support the automation team by clarifying doubts/issues with respect to panel and cameras, which are identified by the automation team 2. Debug the panel and the camera failures by helping automation team | 1. Test Plan 2. Panel: SC 3. Cameras: Ping, dbc, hdc300, hdc400, hd450+bridge | SkyControl | 1. Framework code drop into bitbucket 2. Test automation coverage/report | 4 |  | 2019-06-26 | 2019-07-09
5 | Reliability - 100% Jira tickets: SkyControl_STA_Issues - 50% | Automation Development: 1. Creating the automation procedure/steps/commands for the test cases. 2. Reliability test automation 3. Sniffer module enhancement 4. Unit testing and sanity testing 5. Bug reporting and fixing Test engineer: 1. Regression run. Dev Engineer Support: 1. Support the automation team by clarifying doubts/issues with respect to panel and cameras, which are identified by the automation team 2. Debug the panel and the camera failures by helping automation team | 1. Test Plan 2. Panel: SC 3. Cameras: Ping, dbc, hdc300, hdc400, hd450+bridge | SkyControl | 1. Framework code drop into bitbucket 2. Test automation coverage/report | 5 |  | 2019-07-10 | 2019-07-23
6 | Jira tickets: SkyControl_STA_Issues - 100% Jira tickets: SkyControl_STA_Issues - 100% | Automation Development: 1. Creating the automation procedure/steps/commands for the test cases. 2. JIRA tickets test automation 3. Sniffer module enhancement 4. Unit testing and sanity testing 5. Bug reporting and fixing Test engineer: 1. Regression run. Dev Engineer Support: 1. Support the automation team by clarifying doubts/issues with respect to panel and cameras, which are identified by the automation team 2. Debug the panel and the camera failures by helping automation team | 1. Test Plan 2. Panel: SC 3. Cameras: Ping, dbc, hdc300, hdc400, hd450+bridge | SkyControl | 1. Framework code drop into bitbucket 2. Test automation coverage/report | 6 |  | 2019-07-24 | 2019-08-06
7 | Jira tickets: DBC_Issues - 100% Jira tickets: HDC_Issues - 100% | Automation Development: 1. Creating the automation procedure/steps/commands for the test cases. 2. JIRA tickets test automation 3. Sniffer module enhancement 4. Unit testing and sanity testing 5. Bug reporting and fixing Test engineer: 1. Regression run. Dev Engineer Support: 1. Support the automation team by clarifying doubts/issues with respect to panel and cameras, which are identified by the automation team 2. Debug the panel and the camera failures by helping automation team | 1. Test Plan 2. Panel: SC 3. Cameras: Ping, dbc, hdc300, hdc400, hd450+bridge | SkyControl | 1. Framework code drop into bitbucket 2. Test automation coverage/report | 7 |  | 2019-08-07 | 2019-08-20
8 | Jira tickets: Ping_Issues - 100% Jira tickets: LG-Bridge_Issues - 100% | Automation Development: 1. Creating the automation procedure/steps/commands for the test cases. 2. JIRA tickets test automation 3. Sniffer module enhancement 4. Unit testing and sanity testing 5. Bug reporting and fixing Test engineer: 1. Regression run. Dev Engineer Support: 1. Support the automation team by clarifying doubts/issues with respect to panel and cameras, which are identified by the automation team 2. Debug the panel and the camera failures by helping automation team | 1. Test Plan 2. Panel: SC 3. Cameras: Ping, dbc, hdc300, hdc400, hd450+bridge | SkyControl | 1. Framework code drop into bitbucket 2. Test automation coverage/report | 8 |  | 2019-08-21 | 2019-09-03
9 | 1. Verification and validation of below items on WS, - Sanity - 100% - Functionality - 100% - SnS - 100% - Reliability - 100% | Automation Development: 1. Creating the automation procedure/steps/commands for the test cases. 2. Sanity, Functionality, SnS and Reliability test automation 3. Sniffer module enhancement 4. Unit testing and sanity testing 5. Bug reporting and fixing Test engineer: 1. Regression run. Dev Engineer Support: 1. Support the automation team by clarifying doubts/issues with respect to panel and cameras, which are identified by the automation team 2. Debug the panel and the camera failures by helping automation team | 1. Test Plan 2. Panel: SC 3. Cameras: Ping, dbc, hdc300, hdc400, hd450+bridge | WallSly | 1. Framework code drop into bitbucket 2. Test automation coverage/report | 9 |  | 2019-09-04 | 2019-09-17
10 | 1. Verification and validation of below items on WS, - SkyControl_STA_Issues - 100% - SkyControl_STA_Issues - 100% - DBC_Issues - 100% - HDC_Issues - 100% - Ping_Issues - 100% - LG-Bridge_Issues - 100% | Automation Development: 1. Creating the automation procedure/steps/commands for the test cases. 2. JIRA tickets test automation 3. Sniffer module enhancement 4. Unit testing and sanity testing 5. Bug reporting and fixing Test engineer: 1. Regression run. Dev Engineer Support: 1. Support the automation team by clarifying doubts/issues with respect to panel and cameras, which are identified by the automation team 2. Debug the panel and the camera failures by helping automation team | 1. Test Plan 2. Panel: SC 3. Cameras: Ping, dbc, hdc300, hdc400, hd450+bridge | WallSly | 1. Framework code drop into bitbucket 2. Test automation coverage/report | 10 |  | 2019-09-18 | 2019-10-01

## Auto_Dev_Effort_Estimation
Regression Test Automation Development Effort Estimation per 1 Engineer |  |  |  | Regression Test Automation Development Effort Estimation per 2 Engineers
Work Items | Efforts (In days) | Efforts (In Calendar Months) | High level automation activities | Work Items | Efforts (In days) | Efforts (In Calendar Months) | High level automation activities
88 Test cases (44 Test cases from SC 44 test cases from WS) | 80 | 4 | 1. 5Cameras - Ping, dbc, hdc300, hdc400, hd450+bridge 2. 2 Panels - SkyControl and WallSly 3. Sniffer module enhancement 4. New libraries development - - VLC streaming controlling and meta data parsing. - Multiple cameras handling parallelly. 5. Test suites development and optimization 6. Test report enhancements 7. Framework libraries enhancements 8. Unit testing and integration & sanity testing of libraries 9. Bug fixing 10. Test suites validation on both SC, WS and 5 different cameras (2x5 = 10 combination) 11. 232 tickets to be validated with both SC and WS. | 88 Test cases (44 Test cases from SC 44 test cases from WS) | 50 | 2.5 | 1. 5Cameras - Ping, dbc, hdc300, hdc400, hd450+bridge 2. 2 Panels - SkyControl and WallSly 3. Sniffer module enhancement 4. New libraries development - - VLC streaming controlling and meta data parsing. - Multiple cameras handling parallelly. 5. Test suites development and optimization 6. Test report enhancements 7. Framework libraries enhancements 8. Unit testing and integration & sanity testing of libraries 9. Bug fixing 10. Test suites validation on both SC, WS and 5 different cameras (2x5 = 10 combination) 11. 232 tickets to be validated with both SC and WS.
232 Tickets | 40 | 2 |  | 232 Tickets | 30 | 1.5
Total | 120 | 6 |  | Total | 80 | 4
Note:
1. One Dev and One Test engineers should be required
2. Glance is not considered in above estimation

## SC_TestPlan_Summary
Test Automation Area | Total | Automation Possibilities |  | Current Automation Status (before 15-May-2019)
|  | Automatable | Not automatable | Automated | Not Automated | Partially Automated
Sanity | 8 | 8 | 0 | 1 | 1 | 6
Functionality | 20 | 20 | 0 | 0 | 9 | 11
SnS | 6 | 6 | 0 | 0 | 6 | 0
SkyControl_Reliability | 11 | 10 | 1 | 0 | 0 | 10
Total | 45 | 44 | 1 | 1 | 16 | 27
Tickets | Total | Partially Automated
SkyControl_AP_Issues | 52 | 52
SkyControl_STA_Issues | 78 | 78
DBC_Issues | 30 | 30
HDC_Issues | 35 | 35
Ping_Issues | 23 | 23
LG-Bridge_Issues | 14 | 14
Total | 232 | 232

## WS_TestPlan_Summary
Test Automation Area | Total | Automation Possibilities |  | Current Automation Status (before 15-May-2019)
|  | Automatable | Not automatable | Automated | Not Automated | Partially Automated
Sanity | 8 | 8 | 0 | 1 | 1 | 6
Functionality | 20 | 20 | 0 | 0 | 9 | 11
SnS | 6 | 6 | 0 | 0 | 6 | 0
SkyControl_Reliability | 11 | 10 | 1 | 0 | 0 | 10
Total | 45 | 44 | 1 | 1 | 16 | 27
Tickets | Total | Partially Automated
SkyControl_AP_Issues | 52 | 52
SkyControl_STA_Issues | 78 | 78
DBC_Issues | 30 | 30
HDC_Issues | 35 | 35
Ping_Issues | 23 | 23
LG-Bridge_Issues | 14 | 14
Total | 232 | 232