## SprintPlan
Sl.No | High Level Work Items | Total Test Cases | Automatable Test Cases | Low Level Activities | Panel | Dependencies | Deliverables | Sprints (1 sprint = 2 Weeks) | Status | Start Date | End Date | Release | Backlogs | Remarks
1 | 1. Test plan walkthrough 2. Test bed setup and configuration 3. Porting of existing framework to Smartlab 4. Code optimization and clean up w.r.t Smartlab framework | NA | NA | Automation Development: 1. Test plan walkthrough 2. Test bed setup and configuration 3. Porting of existing framework/lib to Smartlab - Sniffer library - Manager library 4. Code optimization and clean up w.r.t Smartlab framework Testing: 1. Unit testing of libraries 2. Bug reporting and fixing Dev Engineer Support: 1. Support the automation team by clarifying doubts/issues with respect to panel and cameras, which are identified by the automation team 2. Debug the panel and the camera failures by helping automation team to proceed with automation execution | SkyControl | 1. Test plan 2. Smartlab setup 3. SC panel 4. DBC2/DBC2s-250/DBC2s-251 5. Debug module | 1. Unit test report 2. Basic framework code drop in bitbucket 3. Updated test plan with segregation of test cases w.r.t automation 4. List of tasks JIRAs | 1 | Completed | 2018-12-24 | 2018-01-04 | GES_VIVINT_VIDEO_AUTOMATION_V1.0.0 | NO | * GES was off on 25th, Dec because of Christmas
2 | Add/Remove camera | 40 | 26 | Automation Development: 1. Test suite development 2. Framework code porting to Smartlab automation harness Testing: 1. Unit testing of libraries 2. Test execution 3. Bug reporting and fixing Dev Engineer Support: 1. Support the automation team by clarifying doubts/issues with respect to panel and cameras, which are identified by the automation team 2. Debug the panel and the camera failures by helping automation team to proceed with automation execution | SkyControl | 1. Test plan 2. Smartlab setup 3. SC panel 4. DBC2/DBC2s-250/DBC2s-251 5. Debug module | 1. Framework code drop in bitbucket 2. Test suites 3. List of tasks JIRAs 4. Sanity logs | 2 | Completed | 2018-01-07 | 2018-01-18 | GES_VIVINT_VIDEO_AUTOMATION_V2.0.0 | NO | * Due to Makar Sankranti festival, GES will not be working on Jan/15/2019 (Tuesday), hence team will off on that day. * Priority is reduced for Camera firmware upgrade and downgrade feature, this will be taken care in next sprint.
3 | Plug/Unplug camera and panel | 4 | 4 | Automation Development: 1. Test suite development 2. Framework code porting to Smartlab automation harness 3. Library development for plug and unplug operations using switch relay 4. Library development for feature step validations Testing: 1. Unit testing of libraries 2. Test execution 3. Bug reporting and fixing Dev Engineer Support: 1. Support the automation team by clarifying doubts/issues with respect to panel and cameras, which are identified by the automation team 2. Debug the panel and the camera failures by helping automation team to proceed with automation execution | SkyControl | 1. Test plan 2. Smartlab setup 3. SC panel 4. DBC2/DBC2s-250/D BC2s-251 5. Debug module | 1. Framework code drop in bitbucket 2. Test suites 3. List of tasks JIRAs 4. Sanity logs | 3 | Completed | 2018-01-21 | 2018-02-01 | GES_VIVINT_VIDEO_AUTOMATION_V3.0.0 | NO
4 | Factory reset camera | 1 | 1 | Automation Development: 1. Test suite development 2. Framework code porting to Smartlab automation harness 3. Library development for feature step validations Testing: 1. Unit testing of libraries 2. Test execution 3. Bug reporting and fixing Dev Engineer Support: 1. Support the automation team by clarifying doubts/issues with respect to panel and cameras, which are identified by the automation team 2. Debug the panel and the camera failures by helping automation team to proceed with automation execution |  | 1. Test plan 2. Smartlab setup | 1. Framework code drop in bitbucket 2. Test suites 3. List of tasks JIRAs 4. Sanity logs |  | Completed |  |  | NA | Yes | This is not part of the sprint-3. as per agreed assumption those test cases don't have test descriptions, no need to automate them.
5 | Two-way voice call between panel and camera | 6 | 1 | Automation Development: 1. Test suite development 2. Framework code porting to Smartlab automation harness 3. Library development for two-way feature operation including sniffer module 4. Library development for feature step validations Testing: 1. Unit testing of libraries 2. Test execution 3. Bug reporting and fixing Dev Engineer Support: 1. Support the automation team by clarifying doubts/issues with respect to panel and cameras, which are identified by the automation team 2. Debug the panel and the camera failures by helping automation team to proceed with automation execution | SkyControl | 1. Test plan 2. Smartlab setup 3. SC panel 4. DBC2/DBC2s-250/DBC2s-251 5. Debug module | 1. Framework code drop in bitbucket 2. Test suites 3. List of tasks JIRAs 4. Sanity logs |  | Completed |  |  | GES_VIVINT_VIDEO_AUTOMATION_V3.0.0 | NO | 1. 2-way call feature between camera and phone will not be implemented as per agreed discussion
6 | 1. SC panel and Ping camera configuration in the setup. 2. Sprint-3 backlogs implementation 3. WS panel with DBC camera configuration in the setup for NFC feature | - | - | Automation Development: 1. Setup preparation for SC panel and Ping camera 2. Basic ping camera handling library development 3. Spring-3 backlogs implementations - - UT bugs fix- AUTO-5562 - 2-way feature: panel to camera flow - Media clips are generated when user press doorbell button, GES to explore on API/RPC mechanism for this event 4. WallSly handling library development 5. Library development for NFC feature w.r.t DBC camera Testing: 1. Unit testing of libraries 2. Bug reporting and fixing Dev Engineer Support: 1. Support the automation team by clarifying doubts/issues with respect to panel and cameras, which are identified by the automation team 2. Debug the panel and the camera failures by helping automation team to proceed with automation execution | SkyControl WallSly | 1. Test plan 2. Wallsly/SkyControl 3. Ping 4. DBC2/DBC2s-250/DBC2s-251 5. Debug module | 1. Framework code drop in bitbucket 2. Test suites 3. List of tasks JIRAs 4. Sanity logs | 4 | Completed | 2019-02-04 | 2019-02-14 | GES_VIVINT_VIDEO_AUTOMATION_V4.0.0 | NO
7 | 1. Ping and HD300w camera validation with SC panel: a. Add/Remove camera b. Plug/Unplug camera and panel c. Two-way voice call between panel and camera (HD300 camera won't support this feature) d. NFC for ping w.r.t WS | 50 | 39 | Automation Development: 1. Ping and HD300w with SC panel: a. Add/Remove camera b. Plug/Unplug camera c. Two-way voice call between panel and camera d. NFC feature validation for Ping with WS Testing: 1. Unit and Sanity testing 2. Bug reporting and fixing 3. Test suite execution Dev Engineer Support: 1. Support the automation team by clarifying doubts/issues with respect to panel and cameras, which are identified by the automation team 2. Debug the panel and the camera failures by helping automation team to proceed with automation execution | SkyControl WallSly | 1. Test plan 2. SkyControl 3. HD300/Ping 4. Debug module | 1. Framework code drop in bitbucket 2. Test suites 3. List of tasks JIRAs 4. Unit test and Sanity test logs | 5 | Completed | 2019-02-15 | 2019-02-28 | GES_VIVINT_VIDEO_AUTOMATION_V5.0.0 | NO
8 | 1. HD400W and HDP450 cameras validations with SC panel: a. Add/Remove camera b. Plug/Unplug camera and panel | 44 | 30 | Automation Development: 1. HD400W and HDP450 with SC panel: a. Camera firmware downgrade and upgrade b. Camera addition via WPS and Wi-Fi Connect c. On-demand thumbnail generation d. Live video streaming validation (only video) e. Camera power cycle validation f. Panel reboot validation Testing: 1. Unit and Sanity testing 2. Bug reporting and fixing 3. Test suite execution 4. Regression testing Dev Engineer Support: 1. Support the automation team by clarifying doubts/issues with respect to panel and cameras, which are identified by the automation team 2. Debug the panel and the camera failures by helping automation team to proceed with automation execution | SkyControl | 1. Test plan 2. SkyControl 3. HD400/HD450 4. Debug module | 1. Framework code drop in bitbucket 2. Test suites 3. List of tasks JIRAs 4. Unit test and Sanity test logs | 6 | Completed | 2019-03-01 | 2019-03-14 | GES_VIVINT_VIDEO_AUTOMATION_V6.0.0 | HDP450 | 1. Two-way voice call between panel and camera and NFC features are not supported in HD400W and HDP450
9 | 1. Lib development for WallSly panel handling 2. DBC2, DBC2s-250, DBC2s-251 vs WallSly panel - Add/Remove camera - Plug/Unplug camera and panel - Two-way voice call between panel and camera | 50 | 39 | Automation Development: 1. Test suite development for all the requirements 2. Framework code porting to Smartlab automation harness 3. Library integration for all the requirements w.r.t all DBC cameras 4. Library porting for feature step validations Testing: 1. Unit testing of libraries 2. Test execution 3. Bug reporting and fixing Dev Engineer Support: 1. Support the automation team by clarifying doubts/issues with respect to panel and cameras, which are identified by the automation team 2. Debug the panel and the camera failures by helping automation team to proceed with automation execution | WallSly | 1. Test plan 2. Wallsly 3. DBC2/DBC2s-250/DBC2s-251 4. Debug module | 1. Framework code drop in bitbucket 2. Test suites 3. List of tasks JIRAs 4. Unit test and Sanity test logs | 7 | Completed | 2019-03-15 | 2019-03-28 | GES_VIVINT_VIDEO_AUTOMATION_V7.0.0 | NO
10 | 1. HD400, HD450 cameras vs WallSly panel a. Add/Remove camera b. Plug/Unplug camera and panel | 44 | 38 | Automation Development: 1. Test suite development for all the requirements 2. Framework code porting to Smartlab automation harness 3. Library integration for all the requirements w.r.t HD400 and HD450 cameras 4. Library porting for feature step validations Testing: 1. Unit testing of libraries 2. Test execution 3. Bug reporting and fixing 4. Regression testing (all legacy cameras with WS and SK) Dev Engineer Support: 1. Support the automation team by clarifying doubts/issues with respect to panel and cameras, which are identified by the automation team 2. Debug the panel and the camera failures by helping automation team to proceed with automation execution | WallSly | 1. Test plan 2. WallSly 3. HD400/HD450 4. Debug module | 1. Framework code drop in bitbucket 2. Test suites 3. List of tasks JIRAs 4. Unit test and Sanity test logs | 8 | Completed | 2019-03-29 | 2019-04-11 | GES_VIVINT_VIDEO_AUTOMATION_V8.0.0 | NO
11 | 1. HD300w, Ping vs WallSly a. Add/Remove camera b. Plug/Unplug camera and panel c. Two-way voice call between panel and camera (HD300 camera won't support this feature) | 50 | 39 | Automation Development: 1. Test suite development for all the requirements 2. Framework code porting to Smartlab automation harness 3. Library integration for all the requirements w.r.t Ping and HD300w cameras 4. Library porting for feature step validations 5. Merging of the two (init/setup and real test case) nose test cases into one. 6. Sniffer support on intel NUC machine Testing: 1. Unit testing of libraries 2. Test execution 3. Bug reporting and fixing 4. Regression testing (all legacy cameras with WS and SK) Dev Engineer Support: 1. Support the automation team by clarifying doubts/issues with respect to panel and cameras, which are identified by the automation team 2. Debug the panel and the camera failures by helping automation team to proceed with automation execution | WallSly | 1. Test plan 2. WallSly 3. HD300/Ping 4. Debug module | 1. Framework code drop in bitbucket 2. Test suites 3. List of tasks JIRAs 4. Unit test and Sanity test logs | 9 | Completed | 2019-04-12 | 2019-04-25 | GES_VIVINT_VIDEO_AUTOMATION_V9.0.0 | NO
12 | Stabilization/robust/hardening of the tests. | - | - | 1. Code optimization 2. Daily/overnight regressions - Run on WS (both 3.10.16 and 3.19.1) + Ping, DBC, 400, 400, 450 - Run on SC (both 3.10.16 and 3.19.1) + Ping, DBC, 400, 400, 450 3. Jira tickets re-verifications and validations on the latest builds. 4. Follow up with Dev toward ticket fixes | SkyControl WallSly | SkyControl, WallSly, DBC, Ping, HD300w, HDP450, HD400 | 1. Regression test report 2. Provide fix for automation framework issue fix if any | 10 | Completed | 2019-04-26 | 2019-05-09 | GES_VIVINT_VIDEO_AUTOMATION_V10.0.0
13 | Stabilization/robust/hardening of the tests. | - | - | 1. Reset functionality support for LG bridge using relay 2. Workaround support for VID-3800 issue 3. Automation support for camera addition via Ethernet option 4. Daily/overnight regressions - Run on WS (both 3.10.16 and 3.19.1) + Ping, DBC, 400, 400, 450 - Run on SC (both 3.10.16 and 3.19.1) + Ping, DBC, 400, 400, 450 | SkyControl WallSly | SkyControl, WallSly, DBC, Ping, HD300w, HDP450, HD401 | 1. Regression test report 2. Provide fix for automation framework issue fix if any | 11 | Completed | 2019-05-10 | 2019-05-23 | GES_VIVINT_VIDEO_AUTOMATION_V11.0.0
14 | Stabilization/robust/optimization of the tests. | - | - | 1. Automation setup optimization by introducing single intel NUC by replacing the RPI and Sniffer machines 2. Work on VID-3680: ffmpeg hanging issue 3. Camera firmware downgrade – dynamically caching and selecting the camera firmware 4. Negative testing and bug fixing 5. Daily/overnight regressions - Run on WS (both 3.10.16 and 3.19.2/3.19.1) + Ping, DBC, 400, 400, 450 - Run on SC (both 3.10.16 and 3.19.2/3.19.1) + Ping, DBC, 400, 400, 450 6. Replacing ffmpeg with VLC for live video streaming 7. Camera add/delete stress test execution | SkyControl WallSly | SkyControl, WallSly, DBC, Ping, HD300w, HDP450, HD401 | 1. Regression test report 2. Provide fix for automation framework issue fix if any | 12 | Completed | 2019-05-24 | 2019-06-06 | GES_VIVINT_VIDEO_AUTOMATION_V12.0.0
15 | Stabilization/robust/optimization of the tests. | - | - | 1. Replace Wireless module with Wpa_cli, to connect the host to Ping camera 2. Vivit_camera code optimization 3. Merge with Kimo’s code for all the test cases 4. Negative testing 5. Camera add/delete stress test execution 6. Regression tests - cycle-3 a. Run on WS (both 3.19.1 and 3.19.2) + Ping, DBC, 400, 400, 450 b. Run on SC (both 3.19.1 and 3.19.2) + Ping, DBC, 400, 400, 450 | SkyControl WallSly | SkyControl, WallSly, DBC, Ping, HD300w, HDP450, HD401 | 1. Regression test report 2. Provide fix for automation framework issue fix if any | 13 | Completed | 2019-06-07 | 2019-06-20 | GES_VIVINT_VIDEO_AUTOMATION_V13.0.0
16 | Bug fix, Enhancements and optimizatoin of framework | - | - | 1. Regression tests - cycle-4 a. Run on WS (3.19.1) + Ping, DBC, 400, 400, 450 b. Run on SC (3.19.1) + Ping, DBC, 400, 400, 450 2. Camera add/delete stress test execution 3. Enhancing the live video stream functionality with cvlc tool 4. Bug fixes 5. Exploring and validating analytics feature on DBC 6. Negative testing | SkyControl WallSly | SkyControl, WallSly, DBC, Ping, HD300w, HDP450, HD401 | 1. Regression test report 2. Provide fix for automation framework issue fix if any | 14 | Completed | 2019-06-21 | 2019-07-04 | GES_VIVINT_VIDEO_AUTOMATION_V14.0.0
17 | Bug fix, Enhancements of framework, log analysis and execution on SmartLab | - | - | 1. Refactor the code by changing the exceptions to asserts and adding a except block with AssertionError. 2. Provided support for analytics feature on DBC 3. Fetching service_id of primary touchlink device dynamically 4. Regression tests - cycle-5 a. Run on WS (3.19.1/3.19.2) + Ping, DBC, 400, 400, 450 b. Run on SC (3.19.1/3.19.2) + Ping, DBC, 400, 400, 450 5. Tests execution on Smarlab environment remotely, log analysis and issue triaging. 6. Provided framework fixes for the issues observed during execution in Smartlab | SkyControl WallSly | SkyControl, WallSly, DBC, Ping, HD300w, HDP450, HD401 | 1. Regression test report 2. Provide fix for automation framework issue fix if any | 15 | Completed | 2019-07-05 | 2019-07-18 | GES_VIVINT_VIDEO_AUTOMATION_V15.0.0