## Sheet1
Sl No | Activity | Responsibility | Start Date | End Date | Planned Effort | Actual Effort | Status | Remarks
1 | Ipv6
| Understanding & Reading RFC2461 & 2462 | Ramakrishna/Shilpa | 1-05-2017 | 5-05-2017 | 80Hours | 80Hours | Completed
| Made test setup for IPV6 | Ramakrishna | 12-05-2017 | 12-05-2017 | 8Hours | 8Hours | Completed
| Writing test plan for GAP | Ramakrishna | 15-05-2017 | 18-05-2017 | 32Hours | 32Hours | Completed
| Test plan Execution for GAP-WAN | Ramakrishna/Shilpa | 25-05-2017 | 2-06-2017 | 64Hours | 64Hours | Completed
| Test plan Execution for GAP-LAN | Ramakrishna/Shilpa | 19-06-2017 | 29-06-2017 | 112Hours | 112Hours | Completed
| Updating test plan with new test cases | Ramakrishna | 24-07-2017 | 25-07-2017 | 16Hours | 16Hours | Completed
| Execute updated test cases on GAP | Ramakrishna/Shilpa | 31-07-2017 | 4-08-2017 | 40Hours |  | Not started
| Design Automation frame work for IPV6 |  | 21-08-2017 | 21-09-2017 | 160Hours |  | Not started
| Automate the test plan |  | 22-09-2017 |  |  |  | Not started
2 | DHCPV6
| Understanding & Reading RFC3315 & 23633 | Ramakrishna/Shilpa | 8-05-2017 | 12-05-2017 | 80Hours | 80Hours | Completed
| Made test setup for DHCPV6 | Ramakrishna | 24-05-2017 | 24-05-2017 | 8Hours | 8Hours | Completed
| Writing test plan for GAP | Ramakrishna | 19-05-2017 | 23-05-2017 | 32Hours | 32Hours | Completed
| Test plan Execution for GAP-WAN | Ramakrishna/Shilpa | 25-05-2017 | 15-06-2017 | 80Hours | 80Hours | Completed
| Test plan Execution for GAP-LAN | Ramakrishna/Shilpa | 03-07-2017 | 14-07-2014 | 80Hours | 0Hours | Not started | Google AP Not support DHCPV6 server on LAN
| Updating test plan with new test cases | Ramakrishna | 26-07-2017 | 27-07-2017 | 16Hours | 16Hours | Completed
| Execute updated test cases on GAP | Ramakrishna/Shilpa | 07-08-2017 | 11-08-2017 | 40Hours |  | Not started
| Design Automation frame work for DHCPV6 |  | 21-08-2017 | 21-09-2017 | 160Hours |  | Not started
| Automate the test plan |  | 22-10-2017 |  |  |  | Not started
3 | DNSV6
| Understanding & Reading RFC3596 | Ramakrishna/Shilpa | 03-07-2017 | 13-07-2014 | 72Hours | 72Hours | Completed
| Made test setup for IPV6 | Ramakrishna | 14-07-2017 | 14-07-2017 | 8Hours | 8Hours | Completed
| Writing test plan for GAP | Ramakrishna | 30-06-2017 | 30-06-2017 | 8Hours | 8Hours | Completed
| Test plan Execution for GAP-WAN | Ramakrishna/Shilpa | 17-07-2017 | 18-07-2015 | 16Hours | 0Hours | Not started
| Test plan Execution for GAP-LAN | Ramakrishna/Shilpa | 19-07-2017 | 21-07-2015 | 24Hours | 24Hours | Completed
| Updating test plan with new test case | Ramakrishna | 28-07-2017 | 28-07-2017 | 8Hours | 8Hours | Completed
| Execute updated test cases on GAP | Ramakrishna/Shilpa | 16-07-2017 | 18-08-2017 | 24Hours |  | Not started
| Design Automation frame work for DNSV6 |  | 21-08-2017 | 21-09-2017 | 160Hours |  | Not started
| Automate the test plan |  | 22-11-2017 |  |  |  | Not started